## WBSData
WBS | Name | Duration | Predecessors | Resource Names
NPLA | New Product Launch | 166d
NPLA.1 | Read the note for an explanation of the purpose of this template | 0d
NPLA.2 | Phase 1 - Planning | 18d
NPLA.2.1 | Identify the launch team | 4d | 2 | Engineering,Manufacturing,Marketing,Sales,Product Support,Field Service,Product Manager
NPLA.2.2 | Determine sales objectives | 3d | 4 | Product Manager
NPLA.2.3 | Define launch goals (launch timing and publicity objectives) | 5d | 5 | Product Manager
NPLA.2.4 | Identify channel partners | 6d | 6 | Marketing
NPLA.2.5 | Identify retail partners | 4d | 7SS | Marketing
NPLA.2.6 | Identify online opportunities | 4d | 8SS
NPLA.2.7 | Identify budget requirements | 3d | 9SS | Marketing
NPLA.2.8 | Obtain launch budget approval | 2d | 10SS | Product Manager
NPLA.3 | Phase 2 - Initiation | 21d
NPLA.3.1 | Kickoff product launch | 1d | 7,8,9,10,11 | Product Manager
NPLA.3.2 | Define creative brief | 2d | 13 | Product Manager
NPLA.3.3 | Review current literature and plan new requirements | 3d | 14SS | Marketing
NPLA.3.4 | Define press release requirements | 3d | 15SS | Marketing
NPLA.3.5 | Define product specification literature | 3d | 16SS
NPLA.3.6 | Define sales presentations | 2d | 17SS | Marketing
NPLA.3.7 | Define internal communication needs | 3d | 18SS | Marketing
NPLA.3.8 | Align product release timing with marketing plan | 1d | 19,14,15,16,17,18 | Engineering
NPLA.3.9 | Prepare for volume manufacturing according to sales goals | 2d | 20 | Manufacturing
NPLA.3.10 | Plan sales force staffing and training to support sales goals | 3d | 21 | Sales
NPLA.3.11 | Plan team staffing to support sales goals | 4d | 22 | Product Support
NPLA.3.12 | Plan field service staffing to support sales goals | 3d | 23 | Field Service
NPLA.3.13 | Supply updated requirements and budgets based on departmental plans | 2d | 24 | Engineering,Manufacturing,Marketing,Sales,Product Support,Field Service
NPLA.3.14 | Obtain approval for updated plans and budgets. | 2d | 25 | Product Manager
NPLA.4 | Phase 3 - Execution | 52d
NPLA.4.1 | Marketing | 29d
NPLA.4.1.1 | Evaluate market and refine messaging | 2d | 26 | Marketing
NPLA.4.1.2 | Design and order final packaging | 20d | 29 | Marketing
NPLA.4.1.3 | Create press releases | 7d | 30 | Marketing
NPLA.4.1.4 | Create product specification literature | 2d | 31SS | Marketing
NPLA.4.1.5 | Create sales presentations | 2d | 32SS | Marketing
NPLA.4.1.6 | Communicate product launch details to internal organization | 3d | 33SS | Marketing
NPLA.4.1.7 | Create sales, field, and product support training | 3d | 34SS | Marketing
NPLA.4.1.8 | Update product forecasts based on market feedback and analysis | 1d | 35SS | Marketing
NPLA.4.1.9 | Update launch plan based on forecast | 1d | 36 | Marketing
NPLA.4.2 | Engineering | 4d
NPLA.4.2.1 | Complete and test product | 4d | 37,32,33,34,35 | Engineering
NPLA.4.3 | Manufacturing | 8d
NPLA.4.3.1 | Create prototype products | 3d | 39 | Manufacturing
NPLA.4.3.2 | Prepare pipeline | 5d | 41 | Manufacturing
NPLA.4.4 | Sales | 2d
NPLA.4.4.1 | Establish sales channels | 2d | 42 | Sales
NPLA.4.5 | Product Support | 4d
NPLA.4.5.1 | Establish product support mechanisms | 4d | 44 | Product Manager
NPLA.4.6 | Field Service | 4d
NPLA.4.6.1 | Establish field service organizations | 4d | 46 | Field Service
NPLA.4.7 | Prepare for Manufacturing Release | 5d
NPLA.4.7.1 | Implement change control | 3d | 48 | Product Manager
NPLA.4.7.2 | Finalize support policy | 2d | 50 | Product Manager
NPLA.5 | Phase 4 - Release To Manufacture | 75d
NPLA.5.1 | Manufacturing | 25d
NPLA.5.1.1 | Certify product | 20d | 51 | Manufacturing,Product Manager
NPLA.5.1.2 | Manufacture the volume of product planned to meet sales objectives. | 5d | 54 | Manufacturing
NPLA.5.2 | Sales | 10d
NPLA.5.2.1 | Hire and train sales staff | 10d | 55 | Sales
NPLA.5.3 | Product Support | 10d
NPLA.5.3.1 | Hire and train product support personnel | 10d | 57 | Product Support
NPLA.5.4 | Field Service | 10d
NPLA.5.4.1 | Hire and train field service personnel | 10d | 59 | Field Service
NPLA.5.5 | Final Quality Review | 20d
NPLA.5.5.1 | Hire and train field service personnel | 10d | 61 | Engineering,Manufacturing,Marketing,Sales,Product Support,Field Service,Product Manager
NPLA.5.5.2 | Needed materials are on order or in stock. | 10d | 63 | Engineering,Manufacturing,Marketing,Sales,Product Support,Field Service,Product Manager

## Calendar&UnitPrice
Title | Data
Start Date | Today
Work Days | 6 Days Work
Non Working Day | Friday
Work Start Time | 8:00
Work End Time | 17:00
Hours peer day | 8 H
Hours peer Week | 48 H
Currency | ریال
Re Cost | All is 10 $ PerHR

## TempData (hidden)
Work- | Baseline Work- | Actual Work- | Work Variance- | Remaining Work- | Cost- | Baseline Cost- | Actual Cost- | Fixed Cost- | Cost Variance- | Remaining Cost- | BCWP- | BCWS- | SV- | Name+ | Notes+ | WBS+ | Constraint Type+ | Constraint Date= | Critical+ | Delay- | Free Slack- | Total Slack- | ID- | Milestone+ | Priority+ | Subproject+ | Baseline Duration- | Actual Duration- | Duration- | Duration Variance- | Remaining Duration- | Percent Complete-[% Complete] | Percent Work Complete-[% Work Complete] | Start= | Finish= | Early Start= | Early Finish= | Late Start= | Late Finish= | Actual Start= | Actual Finish= | Baseline Start= | Baseline Finish= | Start Variance- | Finish Variance- | Predecessors+ | Successors+ | Resource Names+ | Resource Initials+ | Text1+ | Start1= | Finish1= | Text2+ | Start2= | Finish2= | Text3+ | Start3= | Finish3= | Text4+ | Start4= | Finish4= | Text5+ | Start5= | Finish5= | Text6+ | Text7+ | Text8+ | Text9+ | Text10+ | Marked+ | Flag1+ | Flag2+ | Flag3+ | Flag4+ | Flag5+ | Flag6+ | Flag7+ | Flag8+ | Flag9+ | Flag10+ | Rollup+ | CV- | Project+ | Outline Level- | Unique ID- | Number1- | Number2- | Number3- | Number4- | Number5- | Summary+ | Created= | Unique ID Predecessors+ | Unique ID Successors+ | Objects- | Linked Fields+ | Resume= | Stop= | Resume No Earlier Than= | Outline Number+ | Duration1- | Duration2- | Duration3- | Cost1- | Cost2- | Cost3- | Hide Bar+ | Confirmed+ | Update Needed+ | Contact+ | Resource Group+ | ACWP- | Type+ | Recurring+ | Effort Driven+ | Overtime Work- | Actual Overtime Work- | Remaining Overtime Work- | Regular Work- | Overtime Cost- | Actual Overtime Cost- | Remaining Overtime Cost- | Fixed Cost Accrual+ | Hyperlink+ | Hyperlink Address+ | Hyperlink SubAddress+ | Hyperlink Href+ | Assignment+ | Overallocated+ | External Task+ | Subproject Read Only+ | Response Pending+ | TeamStatus Pending+ | Leveling Can Split+ | Level Assignments+ | Work Contour+ | Cost4- | Cost5- | Cost6- | Cost7- | Cost8- | Cost9- | Cost10- | Date1= | Date2= | Date3= | Date4= | Date5= | Date6= | Date7= | Date8= | Date9= | Date10= | Duration4- | Duration5- | Duration6- | Duration7- | Duration8- | Duration9- | Duration10- | Start6= | Finish6= | Start7= | Finish7= | Start8= | Finish8= | Start9= | Finish9= | Start10= | Finish10= | Flag11+ | Flag12+ | Flag13+ | Flag14+ | Flag15+ | Flag16+ | Flag17+ | Flag18+ | Flag19+ | Flag20+ | Number6- | Number7- | Number8- | Number9- | Number10- | Number11- | Number12- | Number13- | Number14- | Number15- | Number16- | Number17- | Number18- | Number19- | Number20- | Text11+ | Text12+ | Text13+ | Text14+ | Text15+ | Text16+ | Text17+ | Text18+ | Text19+ | Text20+ | Text21+ | Text22+ | Text23+ | Text24+ | Text25+ | Text26+ | Text27+ | Text28+ | Text29+ | Text30+ | Assignment Delay- | Assignment Units- | Cost Rate Table+ | Preleveled Start= | Preleveled Finish= | WBS Predecessors+ | WBS Successors+ | Deadline= | Outline Code1+ | Outline Code2+ | Outline Code3+ | Outline Code4+ | Outline Code5+ | Outline Code6+ | Outline Code7+ | Outline Code8+ | Outline Code9+ | Outline Code10+ | Status+ | Physical Percent Complete-[Physical % Complete] | SVPercent- | CVPercent- | Calendar+
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New Product Launch |  | NPLA | As Soon As Possible |  | Yes | 0d | 0d | 0d | 1 | No | Lowest |  | 0d | 0d | 166d | 166d | 166d | 0% | 0% | 2026-05-12 08:00 | 2026-11-21 17:00 | 2026-05-12 08:00 | 2026-11-21 17:00 | 2026-05-12 08:00 | 2026-11-21 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Read the note for an explanation of the purpose of this template |  | NPLA.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 2 | Yes | Lowest |  | 0d | 0d | 0d | 0d | 0d | 0% | 0% | 2026-05-12 08:00 | 2026-05-12 08:00 | 2026-05-12 08:00 | 2026-05-12 08:00 | 2026-05-12 08:00 | 2026-05-12 08:00 |  |  |  |  | 0d | 0d |  | 4 | [22 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | No |  |  | 7 | 0 | No |  |  |  | 1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  |  | NPLA.2.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phase 1 - Planning |  | NPLA.2 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 3 | No | Lowest |  | 0d | 0d | 18d | 18d | 18d | 0% | 0% | 2026-05-12 08:00 | 2026-06-01 17:00 | 2026-05-12 08:00 | 2026-06-01 17:00 | 2026-05-12 08:00 | 2026-06-01 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 3 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Identify the launch team |  | NPLA.2.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 4 | No | Lowest |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2026-05-12 08:00 | 2026-05-16 17:00 | 2026-05-12 08:00 | 2026-05-16 17:00 | 2026-05-12 08:00 | 2026-05-16 17:00 |  |  |  |  | 0d | 0d | 2 | 5 | Engineering,Manufacturing,Marketing,Sales,Product Support,Field Service,Product Manager | E,M,M,S,PS,FS,PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 7 | 0 | 0 | 0 | 0 | 0 | No |  | 1 | 8 | 0 | No |  |  |  | 1.2.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Eng Dept,Maf Dept,Mar Dept,Sal Dept,PrS Dept,FiS Dept,PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.1 | NPLA.2.2 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Determine sales objectives |  | NPLA.2.2 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 5 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-05-17 08:00 | 2026-05-19 17:00 | 2026-05-17 08:00 | 2026-05-19 17:00 | 2026-05-17 08:00 | 2026-05-19 17:00 |  |  |  |  | 0d | 0d | 4 | 6 | Product Manager | PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 8 | 0 | 0 | 0 | 0 | 0 | No |  | 7 | 9 | 0 | No |  |  |  | 1.2.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.2.1 | NPLA.2.3 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Define launch goals (launch timing and publicity objectives) |  | NPLA.2.3 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 6 | No | Lowest |  | 0d | 0d | 5d | 5d | 5d | 0% | 0% | 2026-05-20 08:00 | 2026-05-25 17:00 | 2026-05-20 08:00 | 2026-05-25 17:00 | 2026-05-20 08:00 | 2026-05-25 17:00 |  |  |  |  | 0d | 0d | 5 | 7 | Product Manager | PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 9 | 0 | 0 | 0 | 0 | 0 | No |  | 8 | 10 | 0 | No |  |  |  | 1.2.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.2.2 | NPLA.2.4 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Identify channel partners |  | NPLA.2.4 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 7 | No | Lowest |  | 0d | 0d | 6d | 6d | 6d | 0% | 0% | 2026-05-26 08:00 | 2026-06-01 17:00 | 2026-05-26 08:00 | 2026-06-01 17:00 | 2026-05-26 08:00 | 2026-06-01 17:00 |  |  |  |  | 0d | 0d | 6 | 8SS,13 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 10 | 0 | 0 | 0 | 0 | 0 | No |  | 9 | 11SS,15 | 0 | No |  |  |  | 1.2.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.2.3 | NPLA.2.5[SS],NPLA.3.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Identify retail partners |  | NPLA.2.5 | As Soon As Possible |  | No | 0d | 0d | 2d | 8 | No | Lowest |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2026-05-26 08:00 | 2026-05-30 17:00 | 2026-05-26 08:00 | 2026-05-30 17:00 | 2026-05-28 08:00 | 2026-06-01 17:00 |  |  |  |  | 0d | 0d | 7SS | 9SS,13 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 11 | 0 | 0 | 0 | 0 | 0 | No |  | 10SS | 12SS,15 | 0 | No |  |  |  | 1.2.5 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.2.4[SS] | NPLA.2.6[SS],NPLA.3.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Identify online opportunities |  | NPLA.2.6 | As Soon As Possible |  | No | 0d | 0d | 2d | 9 | No | Lowest |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2026-05-26 08:00 | 2026-05-30 17:00 | 2026-05-26 08:00 | 2026-05-30 17:00 | 2026-05-28 08:00 | 2026-06-01 17:00 |  |  |  |  | 0d | 0d | 8SS | 10SS,13 | [22 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 12 | 0 | 0 | 0 | 0 | 0 | No |  | 11SS | 13SS,15 | 0 | No |  |  |  | 1.2.6 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.2.5[SS] | NPLA.2.7[SS],NPLA.3.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Identify budget requirements |  | NPLA.2.7 | As Soon As Possible |  | No | 0d | 0d | 3d | 10 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-05-26 08:00 | 2026-05-28 17:00 | 2026-05-26 08:00 | 2026-05-28 17:00 | 2026-05-30 08:00 | 2026-06-01 17:00 |  |  |  |  | 0d | 0d | 9SS | 11SS,13 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 13 | 0 | 0 | 0 | 0 | 0 | No |  | 12SS | 14SS,15 | 0 | No |  |  |  | 1.2.7 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.2.6[SS] | NPLA.2.8[SS],NPLA.3.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Obtain launch budget approval |  | NPLA.2.8 | As Soon As Possible |  | No | 0d | 0d | 4d | 11 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-05-26 08:00 | 2026-05-27 17:00 | 2026-05-26 08:00 | 2026-05-27 17:00 | 2026-05-31 08:00 | 2026-06-01 17:00 |  |  |  |  | 0d | 0d | 10SS | 13 | Product Manager | PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 14 | 0 | 0 | 0 | 0 | 0 | No |  | 13SS | 15 | 0 | No |  |  |  | 1.2.8 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.2.7[SS] | NPLA.3.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phase 2 - Initiation |  | NPLA.3 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 12 | No | Lowest |  | 0d | 0d | 21d | 21d | 21d | 0% | 0% | 2026-06-02 08:00 | 2026-06-25 17:00 | 2026-06-02 08:00 | 2026-06-25 17:00 | 2026-06-02 08:00 | 2026-06-25 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 4 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Kickoff product launch |  | NPLA.3.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 13 | No | Lowest |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2026-06-02 08:00 | 2026-06-02 17:00 | 2026-06-02 08:00 | 2026-06-02 17:00 | 2026-06-02 08:00 | 2026-06-02 17:00 |  |  |  |  | 0d | 0d | 7,8,9,10,11 | 14 | Product Manager | PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 15 | 0 | 0 | 0 | 0 | 0 | No |  | 10,11,12,13,14 | 16 | 0 | No |  |  |  | 1.3.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.2.4,NPLA.2.5,NPLA.2.6,NPLA.2.7,NPLA.2.8 | NPLA.3.2 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Define creative brief |  | NPLA.3.2 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 14 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-06-03 08:00 | 2026-06-04 17:00 | 2026-06-03 08:00 | 2026-06-04 17:00 | 2026-06-03 08:00 | 2026-06-04 17:00 |  |  |  |  | 0d | 0d | 13 | 15SS,20 | Product Manager | PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 16 | 0 | 0 | 0 | 0 | 0 | No |  | 15 | 17SS,22 | 0 | No |  |  |  | 1.3.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.1 | NPLA.3.3[SS],NPLA.3.8 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Review current literature and plan new requirements |  | NPLA.3.3 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 15 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-06-03 08:00 | 2026-06-06 17:00 | 2026-06-03 08:00 | 2026-06-06 17:00 | 2026-06-03 08:00 | 2026-06-06 17:00 |  |  |  |  | 0d | 0d | 14SS | 16SS,20 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 17 | 0 | 0 | 0 | 0 | 0 | No |  | 16SS | 18SS,22 | 0 | No |  |  |  | 1.3.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.2[SS] | NPLA.3.4[SS],NPLA.3.8 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Define press release requirements |  | NPLA.3.4 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 16 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-06-03 08:00 | 2026-06-06 17:00 | 2026-06-03 08:00 | 2026-06-06 17:00 | 2026-06-03 08:00 | 2026-06-06 17:00 |  |  |  |  | 0d | 0d | 15SS | 17SS,20 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 18 | 0 | 0 | 0 | 0 | 0 | No |  | 17SS | 19SS,22 | 0 | No |  |  |  | 1.3.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.3[SS] | NPLA.3.5[SS],NPLA.3.8 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Define product specification literature |  | NPLA.3.5 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 17 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-06-03 08:00 | 2026-06-06 17:00 | 2026-06-03 08:00 | 2026-06-06 17:00 | 2026-06-03 08:00 | 2026-06-06 17:00 |  |  |  |  | 0d | 0d | 16SS | 18SS,20 | [22 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 19 | 0 | 0 | 0 | 0 | 0 | No |  | 18SS | 20SS,22 | 0 | No |  |  |  | 1.3.5 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.4[SS] | NPLA.3.6[SS],NPLA.3.8 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Define sales presentations |  | NPLA.3.6 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 18 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-06-03 08:00 | 2026-06-04 17:00 | 2026-06-03 08:00 | 2026-06-04 17:00 | 2026-06-03 08:00 | 2026-06-04 17:00 |  |  |  |  | 0d | 0d | 17SS | 19SS,20 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 20 | 0 | 0 | 0 | 0 | 0 | No |  | 19SS | 21SS,22 | 0 | No |  |  |  | 1.3.6 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.5[SS] | NPLA.3.7[SS],NPLA.3.8 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Define internal communication needs |  | NPLA.3.7 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 19 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-06-03 08:00 | 2026-06-06 17:00 | 2026-06-03 08:00 | 2026-06-06 17:00 | 2026-06-03 08:00 | 2026-06-06 17:00 |  |  |  |  | 0d | 0d | 18SS | 20 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 21 | 0 | 0 | 0 | 0 | 0 | No |  | 20SS | 22 | 0 | No |  |  |  | 1.3.7 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.6[SS] | NPLA.3.8 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Align product release timing with marketing plan |  | NPLA.3.8 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 20 | No | Lowest |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2026-06-07 08:00 | 2026-06-07 17:00 | 2026-06-07 08:00 | 2026-06-07 17:00 | 2026-06-07 08:00 | 2026-06-07 17:00 |  |  |  |  | 0d | 0d | 19,14,15,16,17,18 | 21 | Engineering | E | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 22 | 0 | 0 | 0 | 0 | 0 | No |  | 21,16,17,18,19,20 | 23 | 0 | No |  |  |  | 1.3.8 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Eng Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.7,NPLA.3.2,NPLA.3.3,NPLA.3.4,NPLA.3.5,NPLA.3.6 | NPLA.3.9 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Prepare for volume manufacturing according to sales goals |  | NPLA.3.9 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 21 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-06-08 08:00 | 2026-06-09 17:00 | 2026-06-08 08:00 | 2026-06-09 17:00 | 2026-06-08 08:00 | 2026-06-09 17:00 |  |  |  |  | 0d | 0d | 20 | 22 | Manufacturing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 23 | 0 | 0 | 0 | 0 | 0 | No |  | 22 | 24 | 0 | No |  |  |  | 1.3.9 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Maf Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.8 | NPLA.3.10 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan sales force staffing and training to support sales goals |  | NPLA.3.10 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 22 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-06-10 08:00 | 2026-06-13 17:00 | 2026-06-10 08:00 | 2026-06-13 17:00 | 2026-06-10 08:00 | 2026-06-13 17:00 |  |  |  |  | 0d | 0d | 21 | 23 | Sales | S | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 24 | 0 | 0 | 0 | 0 | 0 | No |  | 23 | 26 | 0 | No |  |  |  | 1.3.10 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Sal Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.9 | NPLA.3.11 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan team staffing to support sales goals |  | NPLA.3.11 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 23 | No | Lowest |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2026-06-14 08:00 | 2026-06-17 17:00 | 2026-06-14 08:00 | 2026-06-17 17:00 | 2026-06-14 08:00 | 2026-06-17 17:00 |  |  |  |  | 0d | 0d | 22 | 24 | Product Support | PS | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 26 | 0 | 0 | 0 | 0 | 0 | No |  | 24 | 27 | 0 | No |  |  |  | 1.3.11 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrS Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.10 | NPLA.3.12 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan field service staffing to support sales goals |  | NPLA.3.12 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 24 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-06-18 08:00 | 2026-06-21 17:00 | 2026-06-18 08:00 | 2026-06-21 17:00 | 2026-06-18 08:00 | 2026-06-21 17:00 |  |  |  |  | 0d | 0d | 23 | 25 | Field Service | FS | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 27 | 0 | 0 | 0 | 0 | 0 | No |  | 26 | 28 | 0 | No |  |  |  | 1.3.12 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | FiS Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.11 | NPLA.3.13 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply updated requirements and budgets based on departmental plans |  | NPLA.3.13 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 25 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-06-22 08:00 | 2026-06-23 17:00 | 2026-06-22 08:00 | 2026-06-23 17:00 | 2026-06-22 08:00 | 2026-06-23 17:00 |  |  |  |  | 0d | 0d | 24 | 26 | Engineering,Manufacturing,Marketing,Sales,Product Support,Field Service | E,M,M,S,PS,FS | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 28 | 0 | 0 | 0 | 0 | 0 | No |  | 27 | 25 | 0 | No |  |  |  | 1.3.13 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Eng Dept,Maf Dept,Mar Dept,Sal Dept,PrS Dept,FiS Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.12 | NPLA.3.14 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Obtain approval for updated plans and budgets. |  | NPLA.3.14 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 26 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-06-24 08:00 | 2026-06-25 17:00 | 2026-06-24 08:00 | 2026-06-25 17:00 | 2026-06-24 08:00 | 2026-06-25 17:00 |  |  |  |  | 0d | 0d | 25 | 29 | Product Manager | PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 25 | 0 | 0 | 0 | 0 | 0 | No |  | 28 | 36 | 0 | No |  |  |  | 1.3.14 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.13 | NPLA.4.1.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phase 3 - Execution |  | NPLA.4 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 27 | No | Lowest |  | 0d | 0d | 52d | 52d | 52d | 0% | 0% | 2026-06-27 08:00 | 2026-08-25 17:00 | 2026-06-27 08:00 | 2026-08-25 17:00 | 2026-06-27 08:00 | 2026-08-25 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 5 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Marketing |  | NPLA.4.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 28 | No | Lowest |  | 0d | 0d | 29d | 29d | 29d | 0% | 0% | 2026-06-27 08:00 | 2026-07-29 17:00 | 2026-06-27 08:00 | 2026-07-29 17:00 | 2026-06-27 08:00 | 2026-07-29 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 29 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.4.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Evaluate market and refine messaging |  | NPLA.4.1.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 29 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-06-27 08:00 | 2026-06-28 17:00 | 2026-06-27 08:00 | 2026-06-28 17:00 | 2026-06-27 08:00 | 2026-06-28 17:00 |  |  |  |  | 0d | 0d | 26 | 30 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 36 | 0 | 0 | 0 | 0 | 0 | No |  | 25 | 37 | 0 | No |  |  |  | 1.4.1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.3.14 | NPLA.4.1.2 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design and order final packaging |  | NPLA.4.1.2 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 30 | No | Lowest |  | 0d | 0d | 20d | 20d | 20d | 0% | 0% | 2026-06-29 08:00 | 2026-07-21 17:00 | 2026-06-29 08:00 | 2026-07-21 17:00 | 2026-06-29 08:00 | 2026-07-21 17:00 |  |  |  |  | 0d | 0d | 29 | 31 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 37 | 0 | 0 | 0 | 0 | 0 | No |  | 36 | 38 | 0 | No |  |  |  | 1.4.1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.1.1 | NPLA.4.1.3 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Create press releases |  | NPLA.4.1.3 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 31 | No | Lowest |  | 0d | 0d | 7d | 7d | 7d | 0% | 0% | 2026-07-22 08:00 | 2026-07-29 17:00 | 2026-07-22 08:00 | 2026-07-29 17:00 | 2026-07-22 08:00 | 2026-07-29 17:00 |  |  |  |  | 0d | 0d | 30 | 32SS | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 38 | 0 | 0 | 0 | 0 | 0 | No |  | 37 | 39SS | 0 | No |  |  |  | 1.4.1.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.1.2 | NPLA.4.1.4[SS] | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Create product specification literature |  | NPLA.4.1.4 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 32 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-07-22 08:00 | 2026-07-23 17:00 | 2026-07-22 08:00 | 2026-07-23 17:00 | 2026-07-22 08:00 | 2026-07-23 17:00 |  |  |  |  | 0d | 0d | 31SS | 33SS,39 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 39 | 0 | 0 | 0 | 0 | 0 | No |  | 38SS | 40SS,45 | 0 | No |  |  |  | 1.4.1.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.1.3[SS] | NPLA.4.1.5[SS],NPLA.4.2.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Create sales presentations |  | NPLA.4.1.5 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 33 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-07-22 08:00 | 2026-07-23 17:00 | 2026-07-22 08:00 | 2026-07-23 17:00 | 2026-07-22 08:00 | 2026-07-23 17:00 |  |  |  |  | 0d | 0d | 32SS | 34SS,39 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 40 | 0 | 0 | 0 | 0 | 0 | No |  | 39SS | 41SS,45 | 0 | No |  |  |  | 1.4.1.5 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.1.4[SS] | NPLA.4.1.6[SS],NPLA.4.2.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Communicate product launch details to internal organization |  | NPLA.4.1.6 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 34 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-07-22 08:00 | 2026-07-25 17:00 | 2026-07-22 08:00 | 2026-07-25 17:00 | 2026-07-22 08:00 | 2026-07-25 17:00 |  |  |  |  | 0d | 0d | 33SS | 35SS,39 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 41 | 0 | 0 | 0 | 0 | 0 | No |  | 40SS | 42SS,45 | 0 | No |  |  |  | 1.4.1.6 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.1.5[SS] | NPLA.4.1.7[SS],NPLA.4.2.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Create sales, field, and product support training |  | NPLA.4.1.7 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 35 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-07-22 08:00 | 2026-07-25 17:00 | 2026-07-22 08:00 | 2026-07-25 17:00 | 2026-07-22 08:00 | 2026-07-25 17:00 |  |  |  |  | 0d | 0d | 34SS | 36SS,39 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 42 | 0 | 0 | 0 | 0 | 0 | No |  | 41SS | 43SS,45 | 0 | No |  |  |  | 1.4.1.7 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.1.6[SS] | NPLA.4.1.8[SS],NPLA.4.2.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update product forecasts based on market feedback and analysis |  | NPLA.4.1.8 | As Soon As Possible |  | No | 0d | 0d | 1d | 36 | No | Lowest |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2026-07-22 08:00 | 2026-07-22 17:00 | 2026-07-22 08:00 | 2026-07-22 17:00 | 2026-07-23 08:00 | 2026-07-23 17:00 |  |  |  |  | 0d | 0d | 35SS | 37 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 43 | 0 | 0 | 0 | 0 | 0 | No |  | 42SS | 44 | 0 | No |  |  |  | 1.4.1.8 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.1.7[SS] | NPLA.4.1.9 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Update launch plan based on forecast |  | NPLA.4.1.9 | As Soon As Possible |  | No | 0d | 0d | 1d | 37 | No | Lowest |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2026-07-23 08:00 | 2026-07-23 17:00 | 2026-07-23 08:00 | 2026-07-23 17:00 | 2026-07-25 08:00 | 2026-07-25 17:00 |  |  |  |  | 0d | 0d | 36 | 39 | Marketing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 44 | 0 | 0 | 0 | 0 | 0 | No |  | 43 | 45 | 0 | No |  |  |  | 1.4.1.9 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Mar Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.1.8 | NPLA.4.2.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Engineering |  | NPLA.4.2 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 38 | No | Lowest |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2026-07-26 08:00 | 2026-07-29 17:00 | 2026-07-26 08:00 | 2026-07-29 17:00 | 2026-07-26 08:00 | 2026-07-29 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 30 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.4.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete and test product |  | NPLA.4.2.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 39 | No | Lowest |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2026-07-26 08:00 | 2026-07-29 17:00 | 2026-07-26 08:00 | 2026-07-29 17:00 | 2026-07-26 08:00 | 2026-07-29 17:00 |  |  |  |  | 0d | 0d | 37,32,33,34,35 | 41 | Engineering | E | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 45 | 0 | 0 | 0 | 0 | 0 | No |  | 44,39,40,41,42 | 46 | 0 | No |  |  |  | 1.4.2.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Eng Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.1.9,NPLA.4.1.4,NPLA.4.1.5,NPLA.4.1.6,NPLA.4.1.7 | NPLA.4.3.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Manufacturing |  | NPLA.4.3 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 40 | No | Lowest |  | 0d | 0d | 8d | 8d | 8d | 0% | 0% | 2026-07-30 08:00 | 2026-08-08 17:00 | 2026-07-30 08:00 | 2026-08-08 17:00 | 2026-07-30 08:00 | 2026-08-08 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 31 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.4.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Create prototype products |  | NPLA.4.3.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 41 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-07-30 08:00 | 2026-08-02 17:00 | 2026-07-30 08:00 | 2026-08-02 17:00 | 2026-07-30 08:00 | 2026-08-02 17:00 |  |  |  |  | 0d | 0d | 39 | 42 | Manufacturing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 46 | 0 | 0 | 0 | 0 | 0 | No |  | 45 | 47 | 0 | No |  |  |  | 1.4.3.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Maf Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.2.1 | NPLA.4.3.2 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Prepare pipeline |  | NPLA.4.3.2 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 42 | No | Lowest |  | 0d | 0d | 5d | 5d | 5d | 0% | 0% | 2026-08-03 08:00 | 2026-08-08 17:00 | 2026-08-03 08:00 | 2026-08-08 17:00 | 2026-08-03 08:00 | 2026-08-08 17:00 |  |  |  |  | 0d | 0d | 41 | 44 | Manufacturing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 47 | 0 | 0 | 0 | 0 | 0 | No |  | 46 | 48 | 0 | No |  |  |  | 1.4.3.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Maf Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.3.1 | NPLA.4.4.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sales |  | NPLA.4.4 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 43 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-08-09 08:00 | 2026-08-10 17:00 | 2026-08-09 08:00 | 2026-08-10 17:00 | 2026-08-09 08:00 | 2026-08-10 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 32 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.4.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Establish sales channels |  | NPLA.4.4.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 44 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-08-09 08:00 | 2026-08-10 17:00 | 2026-08-09 08:00 | 2026-08-10 17:00 | 2026-08-09 08:00 | 2026-08-10 17:00 |  |  |  |  | 0d | 0d | 42 | 46 | Sales | S | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 48 | 0 | 0 | 0 | 0 | 0 | No |  | 47 | 49 | 0 | No |  |  |  | 1.4.4.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Sal Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.3.2 | NPLA.4.5.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Product Support |  | NPLA.4.5 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 45 | No | Lowest |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2026-08-11 08:00 | 2026-08-15 17:00 | 2026-08-11 08:00 | 2026-08-15 17:00 | 2026-08-11 08:00 | 2026-08-15 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 33 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.4.5 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Establish product support mechanisms |  | NPLA.4.5.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 46 | No | Lowest |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2026-08-11 08:00 | 2026-08-15 17:00 | 2026-08-11 08:00 | 2026-08-15 17:00 | 2026-08-11 08:00 | 2026-08-15 17:00 |  |  |  |  | 0d | 0d | 44 | 48 | Product Manager | PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 49 | 0 | 0 | 0 | 0 | 0 | No |  | 48 | 50 | 0 | No |  |  |  | 1.4.5.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.4.1 | NPLA.4.6.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Field Service |  | NPLA.4.6 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 47 | No | Lowest |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2026-08-16 08:00 | 2026-08-19 17:00 | 2026-08-16 08:00 | 2026-08-19 17:00 | 2026-08-16 08:00 | 2026-08-19 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 34 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.4.6 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Establish field service organizations |  | NPLA.4.6.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 48 | No | Lowest |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2026-08-16 08:00 | 2026-08-19 17:00 | 2026-08-16 08:00 | 2026-08-19 17:00 | 2026-08-16 08:00 | 2026-08-19 17:00 |  |  |  |  | 0d | 0d | 46 | 50 | Field Service | FS | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 50 | 0 | 0 | 0 | 0 | 0 | No |  | 49 | 51 | 0 | No |  |  |  | 1.4.6.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | FiS Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.5.1 | NPLA.4.7.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Prepare for Manufacturing Release |  | NPLA.4.7 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 49 | No | Lowest |  | 0d | 0d | 5d | 5d | 5d | 0% | 0% | 2026-08-20 08:00 | 2026-08-25 17:00 | 2026-08-20 08:00 | 2026-08-25 17:00 | 2026-08-20 08:00 | 2026-08-25 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 35 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.4.7 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Implement change control |  | NPLA.4.7.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 50 | No | Lowest |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2026-08-20 08:00 | 2026-08-23 17:00 | 2026-08-20 08:00 | 2026-08-23 17:00 | 2026-08-20 08:00 | 2026-08-23 17:00 |  |  |  |  | 0d | 0d | 48 | 51 | Product Manager | PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 51 | 0 | 0 | 0 | 0 | 0 | No |  | 50 | 52 | 0 | No |  |  |  | 1.4.7.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.6.1 | NPLA.4.7.2 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Finalize support policy |  | NPLA.4.7.2 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 51 | No | Lowest |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2026-08-24 08:00 | 2026-08-25 17:00 | 2026-08-24 08:00 | 2026-08-25 17:00 | 2026-08-24 08:00 | 2026-08-25 17:00 |  |  |  |  | 0d | 0d | 50 | 54 | Product Manager | PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 52 | 0 | 0 | 0 | 0 | 0 | No |  | 51 | 58 | 0 | No |  |  |  | 1.4.7.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.7.1 | NPLA.5.1.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Phase 4 - Release To Manufacture |  | NPLA.5 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 52 | No | Lowest |  | 0d | 0d | 75d | 75d | 75d | 0% | 0% | 2026-08-26 08:00 | 2026-11-21 17:00 | 2026-08-26 08:00 | 2026-11-21 17:00 | 2026-08-26 08:00 | 2026-11-21 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 2 | 6 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.5 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Manufacturing |  | NPLA.5.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 53 | No | Lowest |  | 0d | 0d | 25d | 25d | 25d | 0% | 0% | 2026-08-26 08:00 | 2026-09-23 17:00 | 2026-08-26 08:00 | 2026-09-23 17:00 | 2026-08-26 08:00 | 2026-09-23 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 53 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.5.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Certify product |  | NPLA.5.1.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 54 | No | Lowest |  | 0d | 0d | 20d | 20d | 20d | 0% | 0% | 2026-08-26 08:00 | 2026-09-17 17:00 | 2026-08-26 08:00 | 2026-09-17 17:00 | 2026-08-26 08:00 | 2026-09-17 17:00 |  |  |  |  | 0d | 0d | 51 | 55 | Manufacturing,Product Manager | M,PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 58 | 0 | 0 | 0 | 0 | 0 | No |  | 52 | 59 | 0 | No |  |  |  | 1.5.1.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Maf Dept,PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.4.7.2 | NPLA.5.1.2 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Manufacture the volume of product planned to meet sales objectives. |  | NPLA.5.1.2 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 55 | No | Lowest |  | 0d | 0d | 5d | 5d | 5d | 0% | 0% | 2026-09-19 08:00 | 2026-09-23 17:00 | 2026-09-19 08:00 | 2026-09-23 17:00 | 2026-09-19 08:00 | 2026-09-23 17:00 |  |  |  |  | 0d | 0d | 54 | 57 | Manufacturing | M | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 59 | 0 | 0 | 0 | 0 | 0 | No |  | 58 | 60 | 0 | No |  |  |  | 1.5.1.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Maf Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.5.1.1 | NPLA.5.2.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sales |  | NPLA.5.2 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 56 | No | Lowest |  | 0d | 0d | 10d | 10d | 10d | 0% | 0% | 2026-09-24 08:00 | 2026-10-05 17:00 | 2026-09-24 08:00 | 2026-10-05 17:00 | 2026-09-24 08:00 | 2026-10-05 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 54 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.5.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hire and train sales staff |  | NPLA.5.2.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 57 | No | Lowest |  | 0d | 0d | 10d | 10d | 10d | 0% | 0% | 2026-09-24 08:00 | 2026-10-05 17:00 | 2026-09-24 08:00 | 2026-10-05 17:00 | 2026-09-24 08:00 | 2026-10-05 17:00 |  |  |  |  | 0d | 0d | 55 | 59 | Sales | S | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 60 | 0 | 0 | 0 | 0 | 0 | No |  | 59 | 61 | 0 | No |  |  |  | 1.5.2.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Sal Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.5.1.2 | NPLA.5.3.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Product Support |  | NPLA.5.3 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 58 | No | Lowest |  | 0d | 0d | 10d | 10d | 10d | 0% | 0% | 2026-10-06 08:00 | 2026-10-17 17:00 | 2026-10-06 08:00 | 2026-10-17 17:00 | 2026-10-06 08:00 | 2026-10-17 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 55 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.5.3 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hire and train product support personnel |  | NPLA.5.3.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 59 | No | Lowest |  | 0d | 0d | 10d | 10d | 10d | 0% | 0% | 2026-10-06 08:00 | 2026-10-17 17:00 | 2026-10-06 08:00 | 2026-10-17 17:00 | 2026-10-06 08:00 | 2026-10-17 17:00 |  |  |  |  | 0d | 0d | 57 | 61 | Product Support | PS | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 61 | 0 | 0 | 0 | 0 | 0 | No |  | 60 | 62 | 0 | No |  |  |  | 1.5.3.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | PrS Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.5.2.1 | NPLA.5.4.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Field Service |  | NPLA.5.4 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 60 | No | Lowest |  | 0d | 0d | 10d | 10d | 10d | 0% | 0% | 2026-10-18 08:00 | 2026-10-28 17:00 | 2026-10-18 08:00 | 2026-10-28 17:00 | 2026-10-18 08:00 | 2026-10-28 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 56 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.5.4 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hire and train field service personnel |  | NPLA.5.4.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 61 | No | Lowest |  | 0d | 0d | 10d | 10d | 10d | 0% | 0% | 2026-10-18 08:00 | 2026-10-28 17:00 | 2026-10-18 08:00 | 2026-10-28 17:00 | 2026-10-18 08:00 | 2026-10-28 17:00 |  |  |  |  | 0d | 0d | 59 | 63 | Field Service | FS | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 62 | 0 | 0 | 0 | 0 | 0 | No |  | 61 | 63 | 0 | No |  |  |  | 1.5.4.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | FiS Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.5.3.1 | NPLA.5.5.1 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Final Quality Review |  | NPLA.5.5 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 62 | No | Lowest |  | 0d | 0d | 20d | 20d | 20d | 0% | 0% | 2026-10-29 08:00 | 2026-11-21 17:00 | 2026-10-29 08:00 | 2026-11-21 17:00 | 2026-10-29 08:00 | 2026-11-21 17:00 |  |  |  |  | 0d | 0d | [24 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 3 | 57 | 0 | 0 | 0 | 0 | 0 | Yes |  |  |  | 0 | No |  |  |  | 1.5.5 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  |  | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hire and train field service personnel |  | NPLA.5.5.1 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 63 | No | Lowest |  | 0d | 0d | 10d | 10d | 10d | 0% | 0% | 2026-10-29 08:00 | 2026-11-09 17:00 | 2026-10-29 08:00 | 2026-11-09 17:00 | 2026-10-29 08:00 | 2026-11-09 17:00 |  |  |  |  | 0d | 0d | 61 | 64 | Engineering,Manufacturing,Marketing,Sales,Product Support,Field Service,Product Manager | E,M,M,S,PS,FS,PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 63 | 0 | 0 | 0 | 0 | 0 | No |  | 62 | 65 | 0 | No |  |  |  | 1.5.5.1 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Eng Dept,Maf Dept,Mar Dept,Sal Dept,PrS Dept,FiS Dept,PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.5.4.1 | NPLA.5.5.2 | [12 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Needed materials are on order or in stock. |  | NPLA.5.5.2 | As Soon As Possible |  | Yes | 0d | 0d | 0d | 64 | No | Lowest |  | 0d | 0d | 10d | 10d | 10d | 0% | 0% | 2026-11-10 08:00 | 2026-11-21 17:00 | 2026-11-10 08:00 | 2026-11-21 17:00 | 2026-11-10 08:00 | 2026-11-21 17:00 |  |  |  |  | 0d | 0d | 63 |  | Engineering,Manufacturing,Marketing,Sales,Product Support,Field Service,Product Manager | E,M,M,S,PS,FS,PM | [20 empty] | No | No | No | No | No | No | No | No | No | No | No | No | 0 |  | 4 | 65 | 0 | 0 | 0 | 0 | 0 | No |  | 63 |  | 0 | No |  |  |  | 1.5.5.2 | 0d | 0d | 0d | 0 | 0 | 0 | No | No | No |  | Eng Dept,Maf Dept,Mar Dept,Sal Dept,PrS Dept,FiS Dept,PrM Dept | 0 | Fixed Units | No | Yes | 0h | 0h | 0h | 0h | 0 | 0 | 0 | Prorated |  |  |  |  | No | No | No | No | No | No | No | No | Flat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | No | No | No | No | No | No | No | No | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | NPLA.5.5.1 | [13 empty] | 0% | 0% | 0% | Project Default (Standard)