## Sheet1
No. | Activity | Start Day | Finish Day
1 | Contract Award & Mobilization | 1 | 7
2 | Kick-off Meeting with NWS | 8 | 14
3 | Project Mobilization & Resource Allocation | 8 | 14
Stage A – Inception |  | 57 days
A1 | Data Collection & Document Review | 8 | 28
A2 | Review Existing Studies, GIS, Flow Data & Models | 15 | 35
A3 | MIKE Model Review & SewerGEMS Model Development | 22 | 35
A4 | Methodology, Work Plan & QA/QC Plan | 15 | 35
A5 | Risk Register | 25 | 35
A6 | Inception Report Preparation | 35 | 44
A7 | Submission of Inception Report | 40 | 45
A8 | NWS Review Period | 45 | 59
A9 | Address Comments & Final Approval | 60 | 65
Stage B – Flow Assessment Study |  | 85 days
B1 | Flow Data Compilation & Validation | 40 | 59
B2 | STP & Pump Station Flow Analysis | 50 | 69
B3 | Billing & Population Data Assessment | 50 | 69
B4 | Identification of Suspected Infiltration Zones | 70 | 84
B5 | Selection of Candidate Monitoring Locations | 85 | 94
B6 | Technical Flow Assessment Report | 90 | 104
B7 | Submission | 100 | 105
B8 | NWS Review | 106 | 119
B9 | Comment Resolution & Approval | 120 | 125
Stage C – Site Visits and Field Inspections |  | 65 days
C1 | Site Visit Planning | 90 | 104
C2 | Inspection of Main Collectors & Manholes | 100 | 119
C3 | Pump Station Inspections | 100 | 119
C4 | Identification of Field Investigation Locations | 115 | 124
C5 | Site Visit Report Preparation | 125 | 134
C6 | Submission | 130 | 135
C7 | NWS Review | 136 | 149
C8 | Final Approval | 150 | 155
Stage D – Flow Measurement Campaign + CCTV |  | 155 days
CCTV Inspections |  | 130 | 220
D1 | Installation of Monitoring Systems | 130 | 220
D2 | Field Inspections | 130 | 220
Flow Monitoring, Salinity Sampling & Topographic Surveys Campaign |  | 160 | 260
D3 | Installation of Monitoring Systems | 160 | 260
D4 | Field Inspections | 160 | 260
D5 | Raw & Cleaned Dataset Preparation | 200 | 260
D6 | Monitoring Report Compilation | 200 | 260
D7 | Submission | 261 | 265
D8 | NWS Review | 266 | 279
D9 | Final Acceptance | 280 | 285
Stage E – Hydraulic Modelling |  | 100 days
E1 | SewerGEMS Model Update | 250 | 280
E2 | Model Calibration | 281 | 300
E3 | Capacity Assessment | 301 | 320
E4 | Baseline Scenario Modelling | 301 | 324
E5 | Reduced Infiltration Scenario Modelling | 301 | 324
E6 | Calibration & Validation Report Submission | 325 | 330
E7 | NWS Review | 330 | 344
E8 | Final Approval | 345 | 350
Stage F – Infiltration Reduction Study & Strategic Roadmap |  | 85 days
F1 | Comprehensive Review & Assessment of Project Findings | 280 | 320
F2 | Development of Mitigation Measures | 290 | 335
F3 | Prioritization of Interventions | 295 | 340
F4 | CAPEX/OPEX Assessment | 300 | 340
F5 | Strategic Roadmap Development | 300 | 340
F6 | Infiltration Reduction Study Report | 340 | 345
F7 | Submission | 246 | 359
F8 | NWS Review | 360 | 365
F9 | Final Submission & Project Close-Out | 365 | 365