## 100
VENDOR PRINT INDEX & SCHEDULE
LEGEND OF REVIEW CODE
contract No. |  | JPC-1401-35 | ISSUE DATE |  |  | CODE 1 : APPROVED.
CODE 2 : APPROVED WITH COMMENTS. (VENDOR TO AMEND AND SUBMIT THE "FOR APPROVAL")
CODE 3 : COMMENTED. (VENDOR TO AMEND AND SUBMIT THE "FOR APPROVAL")
S/R NO | Vendor Doc No. | DOCUMENT TITLE | Latest Status | Forecast Date |  | Rev 0 |  |  | Rev01 |  |  | Rev02 |  |  | Rev03 |  |  | Rev04 |  |  | Rev05 |  |  | Rev06 |  |  | Rev07 |  |  | Rev08 |  |  | Rev09 |  |  | Rev10 |  |  | Rev11 |  |  | Rev12 |  |  | Rev13
| Purchaser Doc No. |  |  |  |  | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review | Vendor | Transmital No | Review
[6 empty] | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code | Purchaser | Comment Sheet No. | Code
General
1 | ESP-E-VDI-1258-001 | Vendor's Document Index & Schedule (VDIS) | AP | 1401-08-10 |  | 11.01.22 | 2 | FA | 04.18.23 | 48 | FA | 10.31.23 | 134 | FA | 01.20.24 | 152 | FA | 02.28.24 | 191 | FA
| 0135-JPC-ESP-PJ-INX-001 |  |  |  |  | 11.06.22 | 2 | AP | 04.24.23 | 48 | CM | 11.12.23 | 134 | AP | 01.23.24 | 152 | AP | 03.02.24 | 191 | AP
2 | ESP-E-LIS-1258-001 | Sub-Vedors List | AP | 2022/11/15 1401-08-24 |  | 10.31.23 | 135 | FA | 01.21.24 | 155 | FA | 10.31.23 | 135 | FA
| 0135-JPC-ESP-PJ-LST-001 |  |  |  |  | 11.12.23 | 135 | CM | 01.24.24 | 155 | AP | 11.12.23 | 135 | AP
3 | ESP-E-LIS-1258-002 | Manufacturing Data Book Index |  | -
0135-JPC-ESP-PJ-INX-002
4 | ESP-E-VDB-1258-001 | Manufacturing Data Book |  | -
0135-JPC-ESP-PJ-DB-001
5 | ESP-E-SCH-1258-001 | Time Schedule | AP | 2022/11/02 1401-08-11 | [7 empty] | 10.18.22 | 1 | FA | 11.02.22 | 3 | FA | 11.07.22 | 5 | FA | 12.24.22 | 8 | CM | 06.19.23 | 79 | FA | 08.19.23 | 104 | FA | 01.13.24 | 147 | FA | 05.28.24 | 211 | FA | 07.02.24 | 220 | FA | 07.22.24 | 224 | FA | 08.18.24 | 230 | FA | 08.22.24 | 236 | FA
| 0135-JPC-ESP-PL-INX-001 | [10 empty] | 10.25.22 | 1 | CM | 11.12.22 | 3 | CM | 11.12.22 | 5 | CM | 01.07.23 | 8 | AP | 07.24.23 | 79 | CM | 08.22.23 | 104 | AP | 01.29.24 | 147 | AP | 06.10.24 | 211 | CM | 07.08.24 | 220 | CM | 07.24.24 | 224 | CM | 08.19.24 | 230 | CM | 09.07.24 | 236 | AP
6 | ESP-E-WBS-1258-001 | Work Breakdown Structure (WBS) | AP | 2022/11/02 1401-08-11 |  |  |  |  | 10.18.22 | 1 | FA | 11.02.22 | 4 | FA | 01.16.24 | 149 | FA | 05.28.24 | 212 | FA | 07.02.24 | 220 | FA | 07.22.24 | 224 | FA | 08.18.24 | 230 | FA | 08.22.24 | 237 | FA
| 0135-JPC-ESP-PL-INX-002 | [7 empty] | 10.25.22 | 1 | CM | 11.20.22 | 4 | AP | 01.16.29 | 149 | AP | 06.10.24 | 212 | CM | 07.08.24 | 220 | CM | 07.24.24 | 224 | CM | 08.19.24 | 230 | CM | 09.07.24 | 237 | AP
7 | ESP-E-CBS-1258-001 | Cost Breakdown Structure (CBS) | AP | 2022/11/02 1401-08-11 |  | 10.18.22 | 1 | FA | 01.05.23 | 9 | FA | 01.16.24 | 149 | FA
| 0135-JPC-ESP-PL-INX-003 |  |  |  |  | 11.20.22 | 1 | CM | 01.07.23 | 9 | AP | 01.16.29 | 149 | AP
INSTRUMENT
8 | ESP-E-LIS-1258-003 | Instrument Index | AP | 2022-12.06 1401-09-15 |  | 07.12.23 | 84 | FA | 01.15.24 | 145 | FA
| 0135-JPC-ESP-IN-INX-001 |  |  |  |  | 07.12.23 | 84 | AN | 01.15.24 | 145 | AP
10 | ESP-E-DSH-1258-001 | Analayzer Data Sheet | AP | 2022-12-13 1401-09-22 |  | 04.18.23 | 43 | FA | 04.16.23 | 51 | FA | 01.22.24 | 159 | FA
| 0135-JPC-ESP-IN-DSH-001 |  |  |  |  | 05.06.23 | 43 | CM | 05.17.23 | 51 | CM | 01.23.24 | 159 | AP
11 | ESP-E-DSH-1258-002 | Control Valve Data Sheet | AP | 2022-12-13 1401-09-22 |  | 04.18.23 | 47 | FA | 05.16.23 | 53 | FA | 07.03.23 | 82 | FA | 01.22.24 | 157 | FA | 02.04.24 | 169 | FA
| 0135-JPC-ESP-IN-DSH-002 |  |  |  |  | 05.06.23 | 47 | CM | 06.14.23 | 53 | CM | 07.05.23 | 82 | AN | 01.24.24 | 157 | AN | 02.18.24 | 169 | AP
12 | ESP-E-DSH-1258-003 | Flowmeter Data Sheet (Rotameter) | AP | 2022-12-13 1401-09-22 |  | 04.18.23 | 44 | FA | 05.18.23 | 52 | FA | 01.08.24 | 144 | FA | 01.18.24 | 151 | FA
| 0135-JPC-ESP-IN-DSH-003 |  |  |  |  | 05.06.23 | 44 | CM | 06.16.23 | 52 | CM | 01.09.24 | 144 | CM | 01.20.24 | 151 | AP
13 | ESP-E-DSH-1258-004 | DP Transmitters (LT,FT,PDT) Data Sheet | AP | 2022-12-13 1401-09-22 |  | 04.18.23 | 45 | FA | 05.16.23 | 56 | FA | 01.08.24 | 144 | FA | 01.18.24 | 151 | FA
| 0135-JPC-ESP-IN-DSH-004 |  |  |  |  | 05.10.23 | 45 | CM | 05.29.23 | 56 | CM | 01.09.24 | 144 | CM | 01.20.24 | 151 | AP
14 | ESP-E-DSH-1258-005 | Orifice Plate Data Sheet | AP | 2022-12-13 1401-09-22 |  | 04.18.23 | 42 | FA | 05.16.23 | 55 | FA | 08.15.23 | 103 | FA | 08.28.23 | 109 | FA
| 0135-JPC-ESP-IN-DSH-005 |  |  |  |  | 05.10.23 | 42 | CM | 05.18.23 | 55 | CM | 08.19.23 | 103 | CM | 08.28.24 | 109 | AP
15 | ESP-E-DSH-1258-006 | On/Off Valve Data Sheet | AP | 2022-12-13 1401-09-22 |  | 04.18.23 | 41 | FA | 05.16.23 | 54 | FA | 06.12.23 | 62 | FA | 07.03.23 | 82 | FA | 01.22.24 | 162 | FA
| 0135-JPC-ESP-IN-DSH-006 |  |  |  |  | 05.09.23 | 41 | NA | 05.22.23 | 54 | CM | 06.18.23 | 62 | CM | 07.05.23 | 82 | AN | 01.23.24 | 162 | AP
16 | ESP-E-DSH-1258-007 | Field Indicator Data Sheet (LG, PI, TI) | AP | 2022-12-13 1401-09-22 |  | 04.18.23 | 46 | FA | 05.16.23 | 57 | FA | 05.29.23 | 67 | FA | 02.12.24 | 173 | FA | 02.12.24 | 175 | FA
| 0135-JPC-ESP-IN-DSH-007 |  |  |  |  | 05.10.23 | 46 | CM | 05.29.23 | 57 | CM | 06.06.23 | 67 | CM | 02.13.24 | 173 | AN | 02.13.24 | 175 | AP
17 | ESP-E-DSH-1258-008 | Pressure Transmitter Data Sheet | AP | 2022-12-13 1401-09-22 |  | 01.08.24 | 144 | FA
| 0135-JPC-ESP-IN-DSH-008 |  |  |  |  | 01.09.24 | 144 | AP
18 | ESP-E-DWG-1258-001 | Instrument Cable and Tray Rout | AP | 2022-12-20 1401-09-29 |  | 04.28.24 | 205 | FA | 05.23.24 | 210 | FA | 06.15.24 | 216 | FA
| 0135-JPC-ESP-IN-DW-001 |  |  |  |  | 04.28.24 | 205 | CM | 05.27.24 | 210 | CM | 06.18.24 | 216 | AP
19 | ESP-E-DWG-1258-002 | Instrument Location Layout | AP | 2022-12-20 1401-09-29 |  | 01.20.24 | 153 | FA | 04.03.24 | 194 | FA | 04.14.24 | 198 | FA
| 0135-JPC-ESP-IN-DW-002 |  |  |  |  | 01.28.24 | 153 | CM | 04.07.24 | 194 | CM | 04.16.24 | 198 | AP
20 | ESP-E-DWG-1258-003 | Instrument Hook Up | AP | 2022-12-13 1401-09-22 |  | 07.30.23 | 92 | FA | 08.03.23 | 97 | FA
| 0135-JPC-ESP-IN-DW-003 |  |  |  |  | 07.31.23 | 92 | CM | 08.09.23 | 97 | AP
21 | ESP-E-DIG-1258-001 | JB WIRING DIAGRAM | AP | 2022-12-13 1401-09-22 |  | 08.31.23 | 114 | FA | 09.14.23 | 117 | FA | 09.25.23 | 121 | FA
| 0135-JPC-ESP-IN-DW-005 |  |  |  |  | 09.12.23 | 114 | CM | 09.25.23 | 117 | CM | 09.26.23 | 121 | AP
22 | ESP-E-DIG-1258-002 | LOOP DIAGRAM | AP | 2022-12-13 1401-09-22 |  | 08.31.23 | 115 | FA | 09.25.23 | 121 | FA | 01.08.24 | 143 | FA | 01.22.24 | 158 | FA
| 0135-JPC-ESP-IN-DW-004 |  |  |  |  | 09.18.2023 | 115 | CM | 09.26.23 | 121 | AP | 01.15.24 | 143 | AP | 01.23.24 | 158 | AP
23 | ESP-E-DIG-1258-001 | Logic Diagram (if applicable) | AP | 2022-12-20 1401-09-29 |  | 09.31.23 | 133 | FA
| 0135-JPC-ESP-IN-DW-006 |  |  |  |  | 10.16.23 | 133 | AP
Electrical
24 | ESP-E-LIS-1258-005 | Electrical Load List | CM | 2022-12-13 1401-09-22 |  | 01.22.24 | 161 | FA | 06.03.24 | 214 | FA | 08.31.24 | 240 | FA
| 0135-JPC-ESP-EL-LST-001 |  |  |  |  | 01.24.24 | 161 | AN | 06.10.24 | 214 | CM | 09.04.24 | 240 | CM
25 | ESP-E-DWG-1258-004 | Earthing Drawing and Installation | AP | 2022-12-20 1401-09-29 |  | 02.24.24 | 184 | FA
| 0135-JPC-ESP-EL-DW-001 |  |  |  |  | 02.28.24 | 184 | AP
26 | ESP-E-DWG-1258-005 | Lighting Drawing and Installation and MTO (if applicable) | AP | 2022-12-20 1401-09-29 |  | 06.23.24 | 218 | FA
| 0135-JPC-ESP-EL-DW-002 |  |  |  |  | 06.24.24 | 218 | AP
27 | ESP-E-DSH-1258-007 | Electro Motor Data Sheet (inculding feeder list) | CM | 2022-12-13 1401-09-22 |  | 09.13.23 | 116 | FA | 09.23.23 | 120 | FA | 08.19.24 | 234 | FA
| 0135-JPC-ESP-EL-DSH-001 |  |  |  |  | 09.17.23 | 116 | CM | 09.30.23 | 120 | CM | 08.25.24 | 234 | CM
28 | ESP-E-DWG-1258-006 | Cable Power and Control Rout | AP | 2022-12-20 1401-09-29 |  | 07.08.24 | 221 | FA | 08.20.24 | 235 | FA | 08.28.24 | 239 | FA
| 0135-JPC-ESP-EL-DW-003 |  |  |  |  | 07.09.24 | 221 | AN | 08.25.24 | 235 | AN | 08.29.24 | 239 | AP
Process
30 | ESP-E-MNL-1258-001 | Process Description | AP | 2022/11/15 1401-08-24 |  | 01.21.23 | 13 | FA | 06.08.23 | 70 | FA
| 0135-JPC-ESP-PR-MNL-001 |  |  |  |  | 01.01.23 | 13 | NA | 06.10.23 | 70 | AP
31 | ESP-E-PFD-1258-001 | PFD, Heat and Material Balance | AP | 2022/11/08 1401-08-17 |  | 12.10.22 | 7 | FA | 01.28.23 | 19 | FA | 03.07.23 | 28 | FA | 04.15.23 | 33 | FA | 08.03.23 | 95 | FA | 08.30.23 | 111 | FA
| 0135-JPC-ESP-PR-PFD-001 |  |  |  |  | 12.24.22 | 7 | CM | 01.31.23 | 19 | CM | 03.13.23 | 28 | CM | 04.29.23 | 33 | AN | 08.12.23 | 95 | AN | 09.04.23 | 111 | AP
32 | ESP-E-PID-1258-001 | P&ID | AP | 2022/11/15 1401-08-24 |  | 12.07.22 | 6 | FA | 01.28.23 | 18 | FA | 03.07.23 | 29 | FA | 04.16.23 | 34 | FA | 06.12.23 | 78 | FA | 10.26.23 | 129 | FA | 02.19.24 | 150 | FA
| 0135-JPC-ESP-PR-PID-001 |  |  |  |  | 12.14.22 | 6 | CM | 02.01.23 | 18 | CM | 03.13.23 | 29 | CM | 04.25.23 | 34 | CM | 06.17.23 | 78 | ( UPDATE REV 4) CM | 01.03.24 | 129 | AN | 02.20.24 | 150 | AP
33 | ESP-E-DSH-1258-008 | Process Datasheet for PPI 10-D-320 | AP | 2022-11-22 1401-09-01 |  | 02.07.23 | 23 | FA | 04.15.23 | 35 | FA | 06.08.23 | 75 | FA
| 0135-JPC-ESP-PR-DSH-001 |  |  |  |  | 02.22.23 | 23 | CM | 04.25.23 | 35 | AN | 06.10.23 | 75 | AP
34 | ESP-E-DSH-1258-009 | Process Datasheet for Resin Coalescer 10-D-321A/B | AP | 2022-11-22 1401-09-01 |  | 01.21.23 | 12 | FA | 02.05.23 | 21 | FA | 04.15.23 | 36 | FA | 06.08.23 | 74 | FA | 08.12.23 | 98 | FA
| 0135-JPC-ESP-PR-DSH-002 |  |  |  |  | 01.26.23 | 12 | CM | 02.22.23 | 21 | CM | 04.25.23 | 36 | AN | 06.10.23 | 74 | AP | 09.12.23 | 98 | AP
35 | ESP-E-DSH-1258-010 | Process Datasheet for Filter 10-Z-305A/B | AP | 2022-11-22 1401-09-01 |  | 01.26.23 | 17 | FA | 02.07.23 | 22 | FA | 06.08.23 | 73 | FA
| 0135-JPC-ESP-PR-DSH-003 |  |  |  |  | 02.01.23 | 17 | CM | 02.22.23 | 22 | CM | 06.10.23 | 73 | AP
36 | ESP-E-DSH-1258-011 | Process Datasheet for Mixer 10-Z-303 B | AP | 2022-11-22 1401-09-01 |  | 04.16.23 | 39 | FA | 05.24.23 | 64 | FA | 08.26.23 | 107 | FA | 08.30.23 | 112 | FA
| 0135-JPC-ESP-PR-DSH-004 |  |  |  |  | 04.29.23 | 39 | CM | 06.17.23 | 64 | CM | 08.28.23 | 107 | AN | 09.04.23 | 112 | AP
37 | ESP-E-DSH-1258-012 | Process Datasheet for Drums 10-D-310 B | AP | 2022-11-22 1401-09-01 |  | 01.21.23 | 14 | FA | 04.16.23 | 40 | FA | 06.08.23 | 63 | FA
| 0135-JPC-ESP-PR-DSH-005 |  |  |  |  | 01.26.23 | 14 | CM | 04.29.23 | 40 | CM | 06.10.23 | 63 | AP
38 | ESP-E-DSH-1258-013 | Process Data sheet for Pumps | AP | 2022-11-22 1401-09-01 |  | 04.16.23 | 38 | FA | 05.22.23 | 61 | FA | 06.08.23 | 68 | FA | 02.19.24 | 178 | FA
| 0135-JPC-ESP-PR-DSH-006 |  |  |  |  | 04.29.23 | 38 | CM | 05.29.23 | 61 | CM | 06.10.23 | 68 | AN | 02.28.24 | 178 | AP
39 | ESP-E-CAL-1258-001 | Control valve sizing calculation | AP | 2022-12-13 1401-09-22 |  | 04.16.23 | 30 | FA | 05.22.23 | 60 | FA | 06.12.23 | 66 | FA | 07.03.23 | 82 | FA | 02.04.24 | 169 | FA
| 0135-JPC-ESP-PR-CSH-002 |  |  |  |  | 04.18.23 | 30 | CM | 05.29.23 | 60 | CM | 06.17.23 | 66 | AN | 07.05.23 | 82 | AN | 02.18.24 | 169 | AP
40 | ESP-E-REP-1258-001 | Line sizing calculation report | AP | 2022-12-13 1401-09-22 |  | 04.18.23 | 31 | FA | 11.16.23 | 137 | FA | 01.11.24 | 146 | FA | 02.22.24 | 165 | FA | 03.03.24 | 192 | FA
| 0135-JPC-ESP-PR-CSH-001 |  |  |  |  | 04.29.23 | 31 | CM | 11.29.23 | 137 | CM | 01.14.24 | 146 | AN | 03.03.24 | 165 | AN | 03.03.24 | 192 | AP
41 | ESP-E-MNL-1258-002 | Control philosophy | AP | 2022/11/21 1401-08-30 |  | 02.28.23 | 26 | FA | 06.08.23 | 71 | FA
| 0135-JPC-ESP-PR-MNL-002 |  |  |  |  | 03.06.23 | 26 | CM | 06.10.23 | 71 | AP
42 | ESP-E-MNL-1258-003 | Installation,Maintenance and Operational Manual | AP | 2022/11/21 1401-08-30 |  | 02.28.23 | 27 | FA | 06.08.23 | 72 | FA
| 0135-JPC-ESP-PR-MNL-003 |  |  |  |  | 03.05.23 | 27 | 'CM | 06.10.23 | 72 | AP
43 | ESP-E-LIS-1258-006 | Utility and Consumption List | AP | 2022-11-22 1401-09-01 |  | 06.08.23 | 77 | FA
| 0135-JPC-ESP-PR-LST-001 |  |  |  |  | 06.10.23 | 77 | AP
44 | ESP-E-LIS-1258-007 | Chemical Consumption list (any Chemical, Catalyst, Adsorbent) | AP | 2022-11-22 1401-09-01 |  | 06.08.23 | 76 | FA
| 0135-JPC-ESP-PR-LST-002 |  |  |  |  | 06.10.23 | 76 | AP
45 | ESP-E-MNL-1258-004 | Demulsifier Injection Package 10-PK-303 | CM | 2024-01-20 |  | 02.15.24 | 177 | FA | 3.13.24 | 193 | FA | 04.17.24 | 202 | FA | 05.08.24 | 207 | FA | 08.18.24 | 232 | FA
| 0135-JPC-ESP-PR-MNL-004 |  |  |  |  | 02.28.24 | 177 | CM | 3.18.24 | 193 | CM | 04.23.24 | 202 | CM | 05.15.24 | 207 | CM | 08.25.24 | 232 | CM
Mechanical
45 | ESP-E-LIS-1258-009 | Equipment List | AP | 2022-12-13 1401-09-22 |  | 07.25.23 | 88 | FA | 08.03.23 | 94 | FA | 01.20.24 | 154 | FA | 01.22.24 | 156 | FA
| 0135-JPC-ESP-ME-LST-001 |  |  |  |  | 07.27.23 | 88 | CM | 08.09.23 | 94 | AN | 01.23.24 | 154 | AN | 02.05.24 | 156 | AP
46 | ESP-E-DWG-1258-008 | General and Detail Drawing for PPI 10-D-322 | AP | 2022-12-06 1401-09-15 |  | 02.07.23 | 24 | FA | 26.07.23 | 90 | FA | 08.14.23 | 102 | FA | 08.24.23 | 106 | FA | 04.13.24 | 196 | FA | 06.09.24 | 215 | FA
| 0135-JPC-ESP-ME-DW-002 |  |  |  |  | 02.08.23 | 24 | CM | 13.08.23 | 90 | AN | 08.22.23 | 102 | CM | 08.28.23 | 106 | AN | 04.22.24 | 196 | AN | 06.11.24 | 215 | AP
47 | ESP-E-DWG-1258-009 | General and Detail Drawing for Resin Coalescer 10-D-321 A/B | AP | 2022-12-06 1401-09-15 |  | 01.21.23 | 11 | FA | 07.22.23 | 85 | FA | 08.03.23 | 96 | FA | 08.12.23 | 98 | FA
| 0135-JPC-ESP-ME-DW-003 |  |  |  |  | 01.28.23 | 11 | CM | 07.30.23 | 85 | CM | 08.09.23 | 96 | AN | 08.13.23 | 98 | AP
48 | ESP-E-DWG-1258-010 | General and Detail Drawing for Filter 10-Z-305 A/B | AP | 2022-12-06 1401-09-15 |  | 01.26.23 | 16 | FA | 07.27.23 | 91 | FA | 08..14.23 | 101 | FA | 08.29.23 | 110 | FA | 09.14.23 | 118 | FA | 02.10.20 | 172 | FA
| 0135-JPC-ESP-ME-DW-004 |  |  |  |  | 01.31.23 | 16 | CM | 08.12.23 | 91 | CM | 08.26.23 | 101 | CM | 09.06.23 | 110 | AN | 09.20.23 | 118 | AN | 02.10.24 | 172 | AP
49 | ESP-E-DWG-1258-011 | General and Detail Drawing for Mixer 10-Z-303 B | AP | 2022-12-06 1401-09-15 |  | 05.29.23 | 69 | FA | 07.02.23 | 81 | FA | 08.12.23 | 100 | FA | 10.07.23 | 125 | FA | 12.03.23 | 139 | FA | 12.13.23 | 140 | FA | 02.22.24 | 176 | FA | 28.02.24 | 189 | FA
| 0135-JPC-ESP-ME-DW-005 |  |  |  |  | 06.02.23 | 69 | CM | 07.15.23 | 81 | CM | 09.04.23 | 100 | AN | 12.02.23 | 125 | CM | 23.03.23 | 139 | CM | 12.18.23 | 140 | AN | 02.27.24 | 176 | AN | 05.03.24 | 189 | AP
50 | ESP-E-DWG-1258-012 | General and Detail Drawing for Drum 10-D-310 B | AP | 2022-12-06 1401-09-15 |  | 01.25.23 | 15 | FA | 06.08.23 | 65 | FA | 07.05.23 | 83 | FA | 07.22.23 | 86 | FA | 08.12.23 | 99 | FA | 09.26.23 | 122 | FA | 12.18.23 | 142 | FA | 02.20.24 | 171 | FA
| 0135-JPC-ESP-ME-PCJ-006 |  |  |  |  | 01.28.23 | 15 | CM | 06.18.23 | 65 | CM | 07.15.23 | 83 | AN | 07.26.23 | 86 | AN | 08.26.23 | 99 | AN | 10.07.23 | 122 | AN | 12.26.23 | 142 | AN | 02.21.24 | 171 | AP
51 | ESP-E-DWG-1258-013 | Modification Drawing for 10-TK-302 | AP | 2022-12-06 1401-09-15 |  | 06.27.23 | 80 | FA | 09.26.23 | 122 | FA | 10.29.23 | 130 | FA | 02.05.24 | 170 | FA
| 0135-JPC-ESP-ME-DW-007 |  |  |  |  | 07.01.23 | 80 | CM | 10.07.23 | 122 | CM | 12.06.23 | 130 | AN | 02.07.24 | 170 | AP
52 | ESP-E-DWG-1258-014 | General and Detail Drawing for Pumps | AP | 2022-12-06 1401-09-15 |  | 07.08.24 | 222 | FA | 08.07.24 | 228 | FA
| 0135-JPC-ESP-ME-DW-008 |  |  |  |  | 07.10.24 | 222 | CM | 08.13.24 | 228 | AP
53 | ESP-E-PCR-1258-001 | Pickling & Passivation Procedure | AP | 2022-12-11 1401-09-20 |  | 07.25.23 | 89 | FA
| 0135-JPC-ESP-ME-PCJ-001 |  |  |  |  | 08.12.23 | 89 | AP
54 | ESP-E-DWG-1258-015 | Valve Drawing | AN | 2022-12-11 1401-09-20 |  | 02.12.24 | 174 | FA | 06.18.24 | 217 | FA | 07.22.24 | 225 | FA | 08.27.24 | 237 | FA
| 0135-JPC-ESP-ME-DW-009 |  |  |  |  | 02.14.24 | 174 | CM | 06.24.24 | 217 | CM | 07.28.24 | 225 | AN | 09.11.24 | 237 | AN
Safty
55 | ESP-REP-1258-002 | HAZOP study report | AP | 2022-12-15 1401-09-24 |  | 05.17.23 | 58 | FA
| 0135-JPC-ESP-SA-NRP-001 |  |  |  |  | 06.07.23 | 58 | AP
56 | ESP-E-DWG-1258-016 | Hazardous area classification drawings | AP | 2022-12-15 1401-09-24 |  | 01.22.24 | 163 | FA | 02.24.24 | 185 | FA
| 0135-JPC-ESP-SA-DW-002 |  |  |  |  | 01.24.24 | 163 | AN | 02.28.24 | 185 | AP
Piping
57 | ESP-E-REP-1258-002 | 3D Piping Model Review Report | AN | 2022-12-11 1401-09-20 |  | 05.20.23 | 59 | FA | 09.27.23 | 123 | FA | 11.12.23 | 136 | FA | 01.15.24 | 148 | FA | 01.27.24 | 166 | FA | 05.20.24 | 209 | FA
| 0135-JPC-ESP-PI-DW-001 |  |  |  |  | 05.31.23 | 59 | CM | 10.04.23 | 123 | CM | 11.21.23 | 136 | CM | 01.16.24 | 148 | AN | 02.06.24 | 166 | AN | 05.27.24 | 209 | AN
58 | ESP-E-REP-1258-003 | Piping Felexibity and Stress Analysis Calculation Report | AP | 2022-12-11 1401-09-20 |  | 02.19.24 | 179 | FA | 16.04.23 | 199 | FA | 04.22.24 | 203 | FA
| 0135-JPC-ESP-PI-CSH-001 |  |  |  |  | 02.21.24 | 179 | CM | 20.04.23 | 199 | AN | 04.27.24 | 203 | AP
59 | ESP-E-MTO-1258-001 | MTO for Pipes and Piping Components | AP | 2022-12-11 1401-09-20 |  | 01.28.24 | 167 | FA | 08.19.24 | 233 | FA
| 0135-JPC-ESP-PI-MTO-003 |  |  |  |  | 06.02.24 | 167 | CM | 08.21.24 | 233 | AP
60 | ESP-E-LIS-1258-010 | Tie-in point and interface list | AP | 2022-12-31 |  | 01.24.24 | 153 | FA | 02.24.24 | 186 | FA | 02.28.24 | 190 | FA
| 0135-JPC-ESP-PI-LST-001 |  |  |  |  | 01.28.24 | 153 | CM | 02.27.24 | 186 | AN | 03.04.24 | 190 | AP
61 | ESP-E-PPL-1258-016 | Piping Plan & Layout | AP | 2022-12-11 1401-09-20 |  | 02.26.24 | 187 | FA | 04.18.24 | 201 | FA
| 0135-JPC-ESP-PI-DW-002 |  |  |  |  | 04.03.24 | 187 | CM | 04.27.24 | 201 | AP
62 | ESP-E-DWG-1258-017 | Piping isometric drawings | AN | 2022-12-11 1401-09-20 |  | 02.03.24 | 168 | FA | 04.07.24 | 195 | FA
| 0135-JPC-ESP-PI-DW-003 |  |  |  |  | 02.14.24 | 168 | CM | 04.15.24 | 195 | AN
63 | ESP-E-DWG-1258-018 | Pipe Support drawings (Standard Pipe Supports) | CM | 2022-12-11 1401-09-20 |  | 02.22.24 | 182 | FA | 05.20.24 | 208 | FA | 08.14.24 | 231 | FA
| 0135-JPC-ESP-PI-DW-004 |  |  |  |  | 04.03.24 | 182 | CM | 05.26.24 | 208 | CM | 08.16.24 | 231 | CM
64 | ESP-E-PPL-1258-001 | Plot Plan | AP | 2023-01-20 1401-10-30 |  | 05.13.23 | 50 | FA | 08.26.23 | 108 | FA | 09.17.23 | 119 | FA | 09.27.23 | 123 | FA | 20.01.24 | 153 | FA | 27.02.24 | 188 | FA | 04.23.24 | 204 | FA
| 0135-JPC-ESP-PI-DW-005 |  |  |  |  | 05.15.23 | 50 | CM | 09.04.23 | 108 | CM | 09.19.23 | 119 | AN | 10.04.23 | 123 | AN | 23.01.24 | 153 | AN | 04.03.24 | 188 | AN | 04.27.24 | 204 | AP
65 | ESP-E-LIS-1258-011 | Line List | AP | 2022-12-11 1401-09-20 |  | 04.16.23 | 32 | FA | 01.22.24 | 160 | FA | 02.22.24 | 183 | FA | 04.13.24 | 197 | FA | 04.17.24 | 200 | FA
| 0135-JPC-ESP-PI-LST-002 |  |  |  |  | 04.18.23 | 32 | CM | 01.24.24 | 160 | CM | 03.02.24 | 183 | CM | 04.15..24 | 197 | AN | 04.22.24 | 200 | AP
66 | ESP-E-LIS-1258-004 | Piping Support List | AP | 2024-24-01 1402-10-23 |  | 08.01.24 | 227 | FA | 08.10.24 | 229 | FA
| 0135-JPC-ESP-PI-LST-003 |  |  |  |  | 08.04.24 | 227 | AN | 08.13.24 | 229 | AP
Inspection
67 | ESP-E-ITP-1258-001 | Inspection & Test Plan (ITP) | AP | 2022-12-11 1401-09-21 |  | 07.25.23 | 87 | FA | 07.31.23 | 93 | FA | 08.19.23 | 105 | FA
| 0135-JPC-ESP-QC-PCJ-001 |  |  |  |  | 07.31.23 | 87 | CM | 08.19.23 | 93 | CM | 08.19.23 | 105 | AP
68 | ESP-E-WBK-1258-001 | Welding Book | AP | 2022-12-11 1401-09-21 |  | 10.08.23 | 126 | FA
| 0135-JPC-ESP-QC-LST-001 |  |  |  |  | 10.20.23 | 126 | AP
69 | ESP-E-PCR-1258-002 | Positive Material Identification (PMI) Procedure | AP | 2022-12-11 1401-09-21 |  | 01.09.23 | 10 | FA | 01.31.23 | 20 | FA
| 0135-JPC-ESP-QC-PCJ-002 |  |  |  |  | 01.28.23 | 10 | CM | 01.31.23 | 20 | AP
70 | ESP-E-PCR-1258-003 | Non-Destructive Examination (NDE) Procedure | AP | 2022-12-11 1401-09-21 |  | 01.09.23 | 10 | FA | 01.31.23 | 20 | FA
| 0135-JPC-ESP-QC-PCJ-003 |  |  |  |  | 01.28.23 | 10 | CM | 01.31.23 | 20 | AP
71 | ESP-E-PCR-1258-004 | Hydrostatic Test Procedure | AP | 2022-12-11 1401-09-21 |  | 01.09.23 | 10 | FA
| 0135-JPC-ESP-QC-PCJ-004 |  |  |  |  | 01.28.23 | 10 | AP
72 | ESP-E-PCR-1258-005 | Painting Procedure | AP | 2022-12-11 1401-09-21 |  | 07.25.23 | 89 | FA | 08.31.23 | 113 | FA | 10.09.23 | 127 | FA
| 0135-JPC-ESP-QC-PCJ-006 |  |  |  |  | 08.12.23 | 89 | CM | 09.06.23 | 113 | CM | 10.11.23 | 127 | AP
73 | ESP-E-PCR-1258-006 | Packing, Marking and Shipping Procedure | AP | 2022-12-11 1401-09-21 |  | 01.09.23 | 10 | FA
| 0135-JPC-ESP-QC-PCJ-007 |  |  |  |  | 01.28.23 | 10 | AP
74 | ESP-E-PCR-1258-007 | PWHT Procedure | AP | 2022-12-11 1401-09-21 |  | 10.07.23 | 124 | FA | 10.29.23 | 131 | FA | 11.22.23 | 138 | FA
| 0135-JPC-ESP-QC-PCJ-008 |  |  |  |  | 10.11.23 | 124 | CM | 11.19.23 | 131 | AN | 12.09.23 | 138 | AP
75 | ESP-E-PCR-1258-009 | Lining Procedure | CM | 2024-24-01 1402-10-23 |  | 02.20.24 | 180 | FA | 08.27.24 | 238 | FA
| 0135-JPC-ESP-QC-PCJ-009 |  |  |  |  | 02.26.24 | 180 | CM | 08.28.24 | 238 | CM
Civil
76 | ESP-E-DWG-1258-019 | Foundation Plan And Loading Data | AP | 2022-12-11 1401-09-20 |  | 10.31.23 | 132 | FA | 12.16.23 | 141 | FA | 01.22.24 | 164 | FA | 20.02.24 | 181 | FA | 05.07.24 | 206 | FA
| 0135-JPC-ESP-CV-DW-001 |  |  |  |  | 11.41.23 | 132 | NA | 12.24.23 | 141 | CM | 02.10.24 | 164 | CM | 06.03.24 | 181 | AN | 05.12.24 | 206 | AP
76 |  | Layout & Detail for Civil Work | AP | 2024-24-01 1402-10-23 |  | 05.31.24 | 213 | FA | 07.02.24 | 220 | FA | 07.18.24 | 223 | FA | 07.29.24 | 226 | FA
| 0135-JPC-ESP-CV-DW-002 |  |  |  |  | 06.08.24 | 213 | CM | 07.10.24 | 220 | CM | 07.23.24 | 223 | CM | 07.31.24 | 226 | AP
Construction and Commissioning Documents
- |  | Detail List Will be Filled in Due Phase |  | -
[5 empty] | تعداد کل مدارک | 76
[5 empty] | تعداد مدارک AP | 66
[5 empty] | تعداد مدارک AN | 3
[5 empty] | تعداد مدارک CM | 5
[5 empty] | تعداد مدارک NOT ISSUED | 2