## Work Schedule
WORK SCHEDULE
Description
|  | STARTING DATE | DURATION(DAYS)
SCOPE OF WORK
1 | SCE request for new service |  | 90
2 | Submittals |  | 90
3 | Pulling Permits |  | 15
4 | Mobilization |  | 5
5 | Construction Neighbor notifications |  | 10
6 | BMP implementing at site |  | 5
7 | Tree removals |  | 10
8 | Tree Relocating |  | 15
9 | Premeter Wall Footings |  | 15
10 | CMU Walls |  | 15
11 | Site Demolition |  | 15
12 | Underground Utilities |  | 25
13 | GeoPier work |  | 10
14 | Building Foundation |  | 30
15 | Steel Structure |  | 20
16 | Concrete Salb |  | 20
17 | Wood Framing and Partition walls |  | 50
18 | Slab on Grade
19 | Column Posts Caisons
20 | Wood Framing
21 | Inside Panels Installation
22 | Door Frame Installation
23 | Outside Railing
24 | Stairs Railing
25 | Plumbing
26 | Electrical
27 | Low Voltage
28 | Communication Lines
29 | Outside Panels Installation
30 | Drywall
31 | Mechanical
32 | Roofing
33 | Site Concrete
34 | Filteration Boxes
35 | Site Furniture
36 | Partitions
37 | Toilet Accesories
38 | Storage Cabinets
39 | Lighting Outside
40 | Lighting Inside
41 | Boat Racks
42 | Outside Paving
43 | Paving Marking
44 | Irigation & Landscape
45 | Cleanups
46 | Electrical conduits |  | 20
47 | Plumbing piping |  | 20
48 | Roofing |  | 20
49 | Sky Light |  | 30
50 | Moisture Barriers |  | 10
51 | Gypsium Board |  | 20
52 | Door Frame Installation |  | 8
53 | Aluminum Doors & Glazing |  | 18
54 | Tile work |  | 9
55 | Painting work |  | 25
56 | Wood Slat |  | 22
57 | Counter Top |  | 5
58 | Cabinet |  | 10
59 | Kitchen Appliance |  | 30
60 | Façade outside walls |  | 21
61 | Site Lights Footings |  | 8
62 | Booster Pump installation |  | 5
63 | Irrigation |  | 60
64 | Site Drains |  | 55
65 | Tree Planting |  | 20
66 | Sewer Line at site |  | 15
67 | Switch Gear and Pedestals |  | 15
68 | Site Walkways |  | 35
69 | Bridge |  | 19
70 | Rip Rap |  | 8
71 | D.G. and Edgers |  | 38
72 | Trash Enclosure |  | 25
73 | Site Furnitures |  | 36
74 | Fences and Gates |  | 30
75 | Street work |  | 17
76 | Final inspection , Punch list corrections |  | 20
77 | Demobization |  | 2
78
79
80
81
34 | Demobilization
Change Order Work