## Control Sheet (2)
PROJECT CONTROL LIST | [16 empty] | On-Hold | 6
[17 empty] | Done | 3
Status Date: | 2025-12-18 | [5 empty] | ّ |  |  |  |  | Follow-Up: |  |  |  |  | In.Progress | 2
[17 empty] | Pending | 5
Task Name | Pile | EXC | Column.Re | Footing.Re | Column.Form | Footing.Form | Column.Conc | Footing.Conc | Beam.Form | Beam rebar | Beam.conc | H.Over | Pedes.Reb | Pedes.Form | Anchor Bolt | Comment
PR-4524 | Done | Done | Done |  | Done |  | Done |  | Done | In.Progress | In.Progress | Pending | [6 empty] | توضیح ستون sch:
PR-4525 | Done | Done | In.Progress |  | In.Progress |  | In.Progress |  | In.Progress | In.Progress | In.Progress | Pending | [6 empty] | اگر 100 بود میزنه done
PR-5301 (FND) | Done | Done | In.Progress |  | In.Progress |  | In.Progress |  | In.Progress | In.Progress | In.Progress | Pending | [6 empty] | اگه اکچوال خورده میزنه inprogress
PR-5301 (ST) | Done | Done | In.Progress |  | In.Progress |  | In.Progress |  | In.Progress | In.Progress | In.Progress | Pending | [6 empty] | اگه صفر بود میزنه pend
PR-5302 (FND) | Done | In.Progress | Pending |  | Pending |  | Pending |  | Pending | Pending | Pending | Pending | [6 empty] | اگه منفی بود میزنه hold
PR-5302 (ST) | Pending | Pending | Pending |  | Pending |  | Pending |  | Pending | Pending | Pending | Pending
STS-5303 | Pending | Pending | Pending |  | Pending |  | Pending |  | Pending | Pending | Pending | Pending
PR-6601 | Done | Done | In.Progress |  | In.Progress |  | Pending |  | Pending | Pending | Pending | Pending
STS-6601 | Done | Done |  | In.Progress |  | In.Progress |  | In.Progress |  |  |  | Pending | In.Progress
STS-6603 | Done | Done |  | Done |  | Done |  | In.Progress |  |  |  | Pending | In.Progress
H-6601 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
H-6602 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
PR-8601
H-8601
H-8602
STS-8601
STS-8603
PR-5202 (FND)
PR-5202 ST
R-5201
TK-5201
SS-40-01
SS-40-02
SS-40-11
RIB-40-04
Tag Total: | Done | In.Progress | On-Hold | Pending |  | Tag Info: | Done | In.Progress | On-Hold | Pending | PR-5202 (FND) |  | 18
Pile | 8 | 0 | 0 | 4 |  | Pile | 0 | 0 | 0 | 0
EXC | 7 | 1 | 0 | 4 |  | EXC | 0 | 0 | 0 | 0
Column.Re | 1 | 4 | 0 | 5 |  | Column.Re | 0 | 0 | 0 | 0
Footing.Re | 1 | 1 | 0 | 2 |  | Footing.Re | 0 | 0 | 0 | 0
Column.Form | 1 | 4 | 0 | 5 |  | Column.Form | 0 | 0 | 0 | 0
Footing.Form | 1 | 1 | 0 | 2 |  | Footing.Form | 0 | 0 | 0 | 0
Column.Conc | 1 | 3 | 0 | 6 |  | Column.Conc | 0 | 0 | 0 | 0
Footing.Conc | 0 | 2 | 0 | 2 |  | Footing.Conc | 0 | 0 | 0 | 0
Beam.Form | 1 | 3 | 0 | 6 |  | Beam.Form | 0 | 0 | 0 | 0
Beam rebar | 0 | 4 | 0 | 6 |  | Beam rebar | 0 | 0 | 0 | 0
Beam.conc | 0 | 4 | 0 | 6 |  | Beam.conc | 0 | 0 | 0 | 0
H.Over | 0 | 0 | 0 | 12 |  | H.Over | 0 | 0 | 0 | 0
Pedes.Reb | 0 | 2 | 0 | 0 |  | Pedes.Reb | 0 | 0 | 0 | 0
Pedes.Form | 0 | 0 | 0 | 0 |  | Pedes.Form | 0 | 0 | 0 | 0
Anchor Bolt | 0 | 0 | 0 | 0 |  | Anchor Bolt | 0 | 0 | 0 | 0
Done
In.Progress
On-Hold
Pending

## Help (hidden)
HELP
https://www.vertex42.com/ExcelTemplates/task-list-template.html |  | © 2017-2019 Vertex42 LLC
About
This task list template provides a simple way to list and track your tasks. It also includes columns for budget and hours. You can delete or add columns and rows as needed. This worksheet was kept simple intentionally. If you would a more advanced way to create a task list for a project, try a Gantt Chart.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
Learn more about Drop-Down Lists
Conditional Formatting
The Priority, % Complete, and Done columns use conditional formatting in different ways. If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
The Done column is updated automatically. When you enter 100% in the % Complete column, the checkmark should appear in the Done column. You can use the drop-down in the Done column if you prefer.
Learn more about Conditional Formatting
Subtotals in the Budget Column
The Total Budget amount uses the SUBTOTAL(9,sum_range) function, that will ignore other SUBTOTAL functions contained within the sum_range.
If you want to create subtotals for each project, you can use the SUBTOTAL(9,sum_range) function.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.

## © (hidden)
Project Task List Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/task-list-template.html
© 2017-2019 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet